ASOKORE MAMPONG MUNICIPAL

2024 ANNUAL ACTION PLAN

MUNICIPAL PLANNING CO-ORDINATING UNIT

OCTOBER 2023

ASOKORE MAMPONG MUNICIPAL ASSEMBLY

2024 ANNUAL ACTION PLAN FOR THE IMPLEMENTATION 2022-2025 MTDP

| S/N | GOAL | ADOPTED MUNICIPAL OBJECTIVES | COMPOSITE ACTIVITIES | LOCATION | TIME FRAME |  |  |  | Funding |  | IMPLEMENTING AGENCY |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | Source of Funding | Estimated Cost | LEAD | COLLABORATING |
| 1 | Improve Local Government and Decentralization | Strengthen fiscal decentralization Improve decentralized planning | Implement the activities of Statistical Dept – Collection of Administrative Data | Asokore Mampong |  |  |  |  | IGF G | 10,000.00 | Dept of Statistics | MPCU |
| 2 |  |  | Organize sub-committee meetings, Executive Committee and General Assembly Meetings | Asokore Mampong |  |  |  |  | IGF G | 60,000.00 | Central Admin. Dept. | Finance Dept |
| 3 |  |  | Preparation of Annual Action Plan, MTDP and Budget and Budget | Asokore Mampong |  |  |  |  | IGF G | 50,000.00 | Central Admin. Dept. | MPCU |
| 4 |  |  | MCE’s Visits to Communities: Organise Town Hall Meetings in the communities | Municipal Wide |  |  |  |  | 1GF CM | 20,000.00 | Information Service Dept | Central Admin. Dept. |
| 5 |  |  | Build the Capacity of Staff and Assembly Members at the National and Local Level (Demand Driven Training Programmes and Workshops) | Asokore Mampong |  |  |  |  | IGF/ DACF/ DACF-RFG G | 80,000.00 | Human Resource Unit | Central Admin. Dept. |
| 6 |  |  | Organise National Day Celebration- Independence, Farmers, Eid-Adha, etc | Municipal Wide |  |  |  |  | IGF/DACF S | 150,000.00 | Central Adm, Dept of Agriculture, | Information Service Dept |
| 7 |  |  | Inauguration of Completed Projects | Municipal Wide |  |  |  |  | IGF CM | 40,000.00 | MPCU | Works Dept |
| 8 |  |  | Monitoring and Evaluation of Programmes and Projects | Municipal Wide |  |  |  |  | DACF/IGF CM | 100,000.00 | MPCU | Central Admin. Dept |
| 9 |  |  | Completion of MCE's Bungalow | Asokore Mampong |  |  |  |  | DACF G | 1,200,000.00 | Works Dept | Central Administration |
| 10 |  |  | Construction of Final Phase of Third Floor of 1. No Two Bedroom Semi-Detached Quarters for Health Staff | Asokore Mampong |  |  |  |  | DACF-RFG S | 1,000,000.00 | Ghana Health Service | Works Department |
| 11 |  |  | Construction of 1 No 2 Bedroom Semi-Detached Quarter Assembly Staff | Asokore Mampong |  |  |  |  | DACF G | 300,000.00 | Works Dept | Central Administration |
| 12 | Create opportunities for all | Enhance inclusive and equitable access to, and participation in quality education at all levels Strengthen school management systems | Renovation of Classroom Blocks, RC Primary School and Garden City Special School | Asokore Mampong, Sepe Dote etc |  |  |  |  | DACF S | 80,000.00 | GES | Works Dept. |
| 13 |  |  | Construction of 1 No 12-Unit Storey Linear Class Room Block with Sanitation Facilities | Nurul -Ameen Senior High School; |  |  |  |  | GETFUND S | 1,000,000.00 | GES | Works Dept. |
| 14 |  |  | Procurement and Supply of 500 Mono Desk to Schools in the Municipality | Municipal Wide |  |  |  |  | DACF-RFG S | 400,000.00 | GES | Works Dept. |
| 15 |  |  | Organise MOCK Exams for BECE Candidate for All Basic Schools in the Municipality | Parkoso SHS |  |  |  |  | IGF S | 20,000.00 | GES | Works Dept. |
| 16 |  |  | Construction of 300 Metre Fence wall | Parkoso SHS |  |  |  |  | DACF S | 80,000.00 | GES | Central Admin Dept. |
| 17 | Create opportunities for all | Improve maternal and adolescent reproductive health Ensure accessible, and quality Universal Health Coverage (UHC) for all | Completion Health Centre | Sawaba |  |  |  |  | DACF-RFG S | 750,000.00 | Ghana Health Service | Works Dept |
| 18 |  |  | Undertake Malaria Control Programme and Immunization Programme | Municipal Wide |  |  |  |  | IGF S | 10,000.00 | Ghana Health Service | Central Admin Dept. |
| 19 |  |  | Conduct public education on HIV/AIDS through the Media, CIC, Churches, Mosque and at community level Annually | Municipal Wide |  |  |  |  | DACF S | 30,000.00 | Ghana Health Service | Central Admin Dept. |
| 20 |  |  | Facilitate the construction municipal hospital (Agenda 111) | Asokore Mampong |  |  |  |  | DACF S | 30,000.00 | Ghana Health Service | Central Admin Dept. |
| 21 |  |  | Supply and Maintenance of Street Light | Municipal Wide |  |  |  |  | DACF/GOG E | 50,000.00 | Works Dept | Central Admin Dept. |
| 22 | Safeguard the natural environment and ensure a resilient built environment | Improve access to safe, reliable and sustainable water supply services for all | Facilitate Extension of Pipe-born water | Buoban Asokore Mampong and Asabi |  |  |  |  | IGF EN | 10,000.00 | Works Dept | Central Admin Dept. |
| 23 |  |  | Construction of 4 Mechanized Boreholes | Municipal Wide |  |  |  |  | DACF-RFG EN | 450,000.00 | Works Dept | Central Admin Dept. |
| 24 |  | Enhance access to improved and sustainable environmental sanitation services | Facilitate Construction of 5 No Gender Friendly Institutional Sanitation Facilities including Water Connection and Solid Waste Management Facilities | Kumasi Academy, Parkoso SHS, Parkoso Primary and Ibadur Rahman SHS |  |  |  |  | SWP AD/IGF EN | 50,000.00 | GAMA S&WP | Works Dept |
| 25 |  |  | Facilitate the Construction of Households Toilets | Municipal Wide |  |  |  |  | SWP AD/IGF EN | 30,000.00 | GAMA S&WP/ | Environmental Health Unit |
| 26 |  |  | Undertake Repairs and maintenance of project vehicles | Municipal Wide |  |  |  |  | IGF G | 60,000,00 | GKMA | Environmental Health Unit |
| 27 |  |  | Conduct Public education on sanitation | Municipal Wide |  |  |  |  | IGF | 10,000.00 | GKMA | Environmental Health Unit |
| 28 |  |  | Undertake Food Vendors Screening and Training | Municipal Wide |  |  |  |  | IGF S | 20,000.00 | Environmental Health Unit | Central Admin Dept. |
| 29 |  |  | Undertake Fumigation Exercise in the Municipality Fumigation | Municipal Wide |  |  |  |  | DACF EN | 120,000.00 | Environmental Health Unit | Works Dept. |
| 30 |  | efficiency and effectiveness of road transport infrastructure and services | Upgrading of Asokore Mampong Kentikrono 3 km Road | Asokore Mampong |  |  |  |  | GOG.GRF EN | 15,000,000.00 | Dept. Of Urban Roads | Works Dept. |
| 31 |  |  | Drainage Works Along Anhyinam Road 4.5 and 5 (1.79) | Asokore Mampong |  |  |  |  | GOG.GRF EN | 4,000,000.00 | Dept. Of Urban Roads | Works Dept. |
| 32 |  |  | Organise Road Traffic and Safety Campaign within the Municipality | Municipal wide |  |  |  |  | IGF EN | 20,000.00 | Transport Department | Works Dept. |
| 33 |  |  | Construction of 3 x 4 Tripple Cell Box Culvert | Sawaba |  |  |  |  | GOG.GRF EN | 2,000,000.00 | Dept. Of Urban Roads | Works Dept. |
| 34 |  |  | Pothole Patching within the Asokore Mampong Municipality | Municipal Wide |  |  |  |  | GOG.GRF EN | 2,000.000.00 | Dept. Of Urban Roads | Works Dept. |
| 35 | Safeguard the natural environment and ensure a resilient built environment | Promote proactive planning for disaster prevention and mitigation | Educate and sensitize the public on fire outbreak | Municipal Wide |  |  |  |  | GOG/IGF EM | 10,000.00 | NADMO | Central Admin Dept. |
| 36 |  |  | Education on pre-flooding and cleaning exercises | Municipal Wide |  |  |  |  | GOG/IGF EM | 10,000.00 | NADMO | Central Admin Dept. |
| 37 |  |  | Planting of 500 Assorted trees | Municipal Wide |  |  |  |  | GOG/IGF EN | 10,000.00 | NADMO | Central Admin Dept. |
| 39 |  |  | Training of Disaster Volunteer Groups (DVGs) | Municipal Wide |  |  |  |  | GOG/IGF EM | 10,000.00 | NADMO | Central Admin Dept. |
| 40 |  |  | Completion of Fire Office Complex | Asokore Mampong |  |  |  |  | DACF EM | 80,000.00 | Fire Service | NADMO |
| 41 | Build a Prosperous Country | Support entrepreneurs and MSME development. | Enhance Literacy Skills of MSMEs 50 operators | Asokore Mampong |  |  |  |  | GEA/IGF/DACF E | 20,000.00 | BAC | Central Admin Dept |
| 42 |  |  | Linking SMEs 50 to Access to Credit | Municipal Wide |  |  |  |  | GEA/IGF/DACF E | 20,000.00 | BAC | Central Admin Dept |
| 43 |  |  | Organise Skilled Apprenticeship Training for 50 Youth Entrepreneurs | Municipal Wide |  |  |  |  | GEA/IGF/DACF E | 20,000.00 | BAC | Central Admin Dept |
| 44 |  |  | Undertake 50 Business Monitoring, Follow-up and counselling and Education Per Quarter | Municipal Wide |  |  |  |  | GEA/IGF/DACF E | 20,000.00 | BAC | Central Admin Dept |
| 45 |  |  | Provide Start-up Kit for 50 Youth Graduate Apprentices | Municipal Wide |  |  |  |  | GEA/IGF/DACF E | 20,000.00 | BAC | Central Admin Dept |
| 46 | Safeguard the natural environment and ensure a resilient built environment | Promote a sustainable, spatially integrated, balanced and orderly development of human settlements | Undertake Street Naming Exercise and House Numbering Exercise | Municipal Wide |  |  |  |  | DACF EN | 40,000.00 | Physical Planning Dept. | Works Dept |
| 47 |  |  | Preparation of Local Plans (Schemes) | Municipal Wide |  |  |  |  | IGF/DACF EN | 10,000.00 | Physical Planning Dept. | Works Dept |
| 48 |  |  | Facilitate Preparation of 3 No Development Schemes (Layout) | Municipal Wide |  |  |  |  | IGF/DACF | 10,000.00 | Physical Planning Dept. | Works Dept |
| 49 |  |  | Preparation of Spatial Development Framework | Municipal Wide |  |  |  |  | IGF/DACF | 10,000.00 | Physical Planning Dept. | Works Dept |
| 50 |  |  | Preparation of Structural Plan for Municipality | Municipal Wide |  |  |  |  | IGF/DACF | 10,000.00 | Physical Planning Dept. | Works Dept |
| 51 |  |  | Organise 12 Number Spatial Planning and Technical Committee Meetings | Asokore Mampong |  |  |  |  | IGF/DACF EN | 10,000.00 | Physical Planning Dept. | Works Dept |
| 52 |  |  | Conduct Field Inspections | Municipal Wide |  |  |  |  | IGF/DACF EN | 10,000.00 | Physical Planning Dept. | Works Dept |
| 53 | Create opportunities for all | Reduce disability, morbidity, and mortality Eradicate poverty in all its forms and dimensions Strengthen social protection, especially for children, women, persons with disability and the elderly | Support the Implementation of LEAP programme in the Municipality | Municipal Wide |  |  |  |  | IGF S | 10,000.00 | Dept. of Social Welfare and Comm. Dev’t. | `Central Admin. Dept. |
| 54 |  |  | Conduct six (6) LEAP payment cycles | Municipal Wide |  |  |  |  | GOG S | - | Dept. of Social Welfare and Comm. Dev’t. | `Central Admin. Dept. |
| 55 |  |  | Organise Review Meeting with selected ISS stakeholders | Municipal Wide |  |  |  |  | UNICEF/ IGF/ GOG S | 2,700.00 | Dept. of Social Welfare and Comm. Dev’t. /MGSP | `Central Admin. Dept. |
| 56 |  |  | Provision of case management services | Municipal Wide |  |  |  |  | UNICEF/ IGF/ GOG S | 5,700.00 | Dept. of Social Welfare and Comm. Dev’t. | `Central Admin. Dept. |
| 57 |  |  | Supporting Case Management in Asokore Mampong Municipal and strengthening referral linkages with other stakeholders (GHS, NHIA, DOVVSU, CHRAG, NGOs etc) | Municipal Wide |  |  |  |  | UNICEF/ IGF/ GOG S | 2,000.00 | Dept. of Social Welfare and Comm. Dev’t. | Central Admin. Dept. GES, GHS |
| 58 |  |  | Management of Twenty-five (25) cases on child and family welfare | Municipal Wide |  |  |  |  | UNICEF/GOG S | 2,000.00 | Central Admin. Dept. | `Central Admin. Dept., GHS, GES |
| 59 |  |  | Sensitization/Community engagement with child protection tool kit in five (5) communities | Municipal Wide |  |  |  |  | UNICEF/GOG S | 6,200.00 | Central Admin. Dept . | `Central Admin. Dept. |
| 60 |  |  | Management of Twenty-five (25) cases on child and family welfare | Municipal Wide |  |  |  |  | GOG S | 2,500.00 | Central Admin. Dept | `Central Admin. Dept. |
| 61 |  |  | Sensitization/Community engagement with child protection tool kids in ten (2) communities | Municipal Wide |  |  |  |  | GOG S | 2,500 | Central Admin. Dept | `Central Admin. Dept |
| 62 |  |  | Conduct Needs For thirty (30) Persons with disability | Municipal Wide |  |  |  |  | GOG | 2,500 | Central Admin Dept | `Central Admin. Dept |
| 63 |  |  | Skill training for thirty (30) Persons with disability | Municipal Wide |  |  |  |  | GOG S | 2, 500 |  | `Central Admin. Dept |
| 64 |  |  | Post Disbursement Monitoring for sixty (60) Persons with Disability | Municipal Wide |  |  |  |  | UNICEF/IGF S | 150,000 | Central Admin Dept. | `Central Admin. Dept |
| 65 |  |  | Assist sixty (60) Persons with Disability with working inputs, Assistive devices, Educational Support and Working Capital | Municipal Wide |  |  |  |  | IGF/ COMMON FUND S | 2,000 | Central Admin | `Central Admin. Dept |
| 66 |  |  | Conduct Needs For thirty (30) Persons with disability | Municipal Wide |  |  |  |  | IGF/ COMMON FUND S | 2,000 | Dept. of Social Welfare and Comm. Dev’t. | `Central Admin. Dept |
| 67 |  |  | Working Visits to Residential Homes for Children | Municipal Wide |  |  |  |  | GOG/ UNICEF S | 800 | Dept. of Social Welfare and Comm. Dev’t. | `Central Admin. Dept |
| 68 |  |  | Supervision and Monitoring of Early Childhood Education Centres | Asokore Mampong and Aboabo |  |  |  |  | GOG/ UNICEF S | 2,000 | Dept. of Social Welfare and Comm. Dev’t. | `Central Admin. Dept |
| 69 |  |  | Working Visits to Residential Homes for Children | Municipal Wide |  |  |  |  | GOG/ UNICEF S | 1,000 | Dept. of Social Welfare and Comm. Dev’t. | `Central Admin. Dept |
| 70 |  |  | Sensitise community members of 100 Homes and 70 stalls/shops | Municipal Wide |  |  |  |  | GOG/ UNICEF S | 1,000 | Dept. of Social Welfare and Comm. Dev’t. | `Central Admin. Dept |
| 71 |  |  | Sensitise and train 3 women’s group on vocational skills | Municipal Wide |  |  |  |  | GOG/ UNICEF E | 7,600 | Dept. of Social Welfare and Comm. Dev’t. | `Central Admin. Dept |
| 72 |  |  | Sensitise 120 homes on flooding and dangers of fire outbreak | Municipal Wide |  |  |  |  | GOG/IGF EN | 5,000.00 | NADMO | `Central Admin. Dept |
| 73 | Build a Prosperous Society Create opportunities for all | Increase Agricultural Productivity Ensure food and nutrition security | Extension Service-Conduct Home and Farm Visits | Municipal Wide |  |  |  |  | GOG/IGF E | 2,000.00 | Dept. of Agriculture | Central Admin. Dept. |
| 74 |  |  | Monitoring visits of Agricultural Operation Visits | Municipal Wide |  |  |  |  | GOG/IGF E | 2,000.00 | Dept. of Agriculture | Central Admin. Dept. |
| 75 |  |  | Celebrate National farmers Day | Municipal Wide |  |  |  |  | GOG/IGF E | 60,000.00 | Dept. of Agriculture | Central Admin. Dept. |
| 76 |  |  | Supply Agricultural Inputs to farmers | Municipal Wide |  |  |  |  | GOG/IGF E | 2,000.00 | Dept. of Agriculture | Central Admin. Dept. |
| 77 | Safeguard the natural environment and ensure a resilient built environment | Reduce environmental pollution | Organize public education on the use LED Bulbs | Municipal Wide |  |  |  |  | IGF EN | 3,000.00 | ECG | MPCU |
| 78 | Safeguard the natural environment and ensure a resilient built environment Build a Prosperous Society | Reduce environmental pollution Diversify and expand the tourism industry for economic development | Organise Public Education on the importance of using LPG Gas | Asokore Mampong |  |  |  |  | GoG/IGF EN | 4,000.00 | MPCU | Central Administration |
| 79 |  |  | Tourism Development -Support the celebration of Id-Fitre and Id-Adha | Municipal Wide |  |  |  |  | GoG/IGF EN | 10,000.00 | MPCU | Central Administration |
| 80 | Build a Prosperous Society | Ensure improved fiscal performance and sustainability | Gazetting of Fee Fixing Resolution | Asokore Mampong |  |  |  |  | IGF E | 50,000.00 | Finance Dept. | Central Admin. Dept. |
| 81 |  |  | Preparation and Submission of Monthly and Annual Financial Statement | Asokore Mampong |  |  |  |  | IGF E | 20,000.00 | Finance Dept. | Central Admin. Dept. |
| 82 |  |  | Implementation of MP Activities | Asokore Mampong |  |  |  |  | MPs DACF | 300,000.00 | Central Admin. Dept. | Finance Department |
| 83 |  |  | Tourism Development of Okomfo Anokye Sword at Asokore Mamong | Asawase Asokore Mampong |  |  |  |  | IGF |  | Centre for Cultural Centre | Central Admin. Dept. |